## Sheet 1 - Asfandyar_VTM_-_Sprin
Sprint_3
Serial # | Use case ID | Test case ID | Test Case description | Test Data | Expected outcome | Actual Outcome | Pass/Fail | Last Tested Date | Tested By | Proof of
1 | UC-S3-01 | TC-S3-01 | Validate goal-setting input logic for numeric fields | Valid/Invalid goal numbers | System accepts valid inputs and shows errors for invalid | System correctly accepted valid goals and displayed proper error messages for invalid inputs. | Pass | 05/22/2025 | Asfandyar | Screenshot of valid/invalid inputs
2 | UC-S3-02 | TC-S3-02 | Test saving and loading weekly goal progress | Sample goal progress values | Progress should be saved and loaded correctly | Goal progress was successfully saved to localStorage and loaded accurately upon reload. | Pass | 05/22/2025 | Asfandyar | Screenshot of saved progress
3 | UC-S3-03 | TC-S3-03 | Run edge-case QA (invalid/empty inputs) | Empty and boundary values | System should reject invalid or empty inputs | System displayed validation warnings and prevented submission of empty or boundary-invalid data. | Pass | 05/22/2025 | Asfandyar | Screenshot of rejection message
4 | UC-S3-04 | TC-S3-04 | Report UI bugs and inconsistencies to dev team | Interface anomalies during use | Bugs should be documented with reproducible steps | Interface bugs were detected and documented with steps to reproduce; no crashes occurred. | Pass | 05/22/2025 | Asfandyar | Bug report submission screenshot