## Sheet1
Project: Personal Habit Tracker Sprint 1
Serial # | Use case ID | Test case ID | Test Case description | Test Data | Expected outcome | Actual Outcome | Pass/Fail | Last Tested Date | Tested By | Proof of by
1 | Kanban Board Setup | TC_Kanban_01 | Verify that a GitHub Kanban board exists and is accessible | GitHub project link: https://github.com/MohamedHussein25/Personal-Habit-Tracker/projects?query=is%3Aopen | Kanban board is created and organized | Board created and tasks visible | Pass | 2025-05-04 | Shiwlee Rahman
2 | Folder Structure | TC_Folder_01 | Check that the project folder includes standard directories and README | Folders: /src, /docs, /test, README.md present in repo | Folders and README are structured correctly | Folders and README in place | Pass | 2025-05-04 | Shiwlee Rahman
3 | Role Assignment | TC_Team_01 | Validate that roles are assigned and documented | Roles listed: Malik (Scrum), Mohammed (Backend), Andrew (Frontend), Shiwlee (QA) | Roles are clearly assigned and visible | Roles listed in project board | Pass | 2025-05-04 | Shiwlee Rahman
4 | Backlog Initialization | TC_Backlog_01 | Ensure at least 6 user stories or tasks are added to the backlog | Kanban board: 6+ tasks created | Backlog has meaningful, clear entries | 6 tasks added with labels | Pass | 2025-05-04 | Shiwlee Rahman
5 | Tech Stack Readiness | TC_Tech_01 | Confirm team alignment on tech stack and feature scope | Notes: React, Node.js, MongoDB; Feature = Habit Tracker | Team is aligned on tools and goals | Confirmed via team sync and chat notes | Pass | 2025-05-04 | Shiwlee Rahman
6 | User Interviews | TC_Interview_01 | Verify that at least 3 user interviews were conducted and results documented | Participants: student, professional, traveler. Format: Notes and video recording | User feedback is structured and informs the feature backlog | Interviews completed and referenced in sprint report | Pass | 2025-05-04 | Shiwlee Rahman